## Sheet1
Developer | ProVia | PilotFish | Features | Description | Launch | Phase 2 | PF Estimate | Notes
|  |  | WordPress Base Design | Create base design used for Design Center and Portfolio pages.
Design Center
|  |  | Configurator | Pop up modal embedding configurators |  |  | 30 | PF will need to meet with Brent to make sure that we can save the state of a configured product via URL.
|  |  | Popular | All items displayed by popularity |  |  |  | It sounds like we may be able to leverage the existing gallery for woo-commerce plugins here. Sean to investigate if this is possible.
|  |  | Project Builder | Drag and drop saved items from wishlist into "cells" to create project |  |  | 120
|  |  | Quizzes | Links to external quizzes outside of design center
|  |  | Color | Tabs displaying "products" by color
|  |  | Palettes | One product being a "collection" containing multiple products within
|  |  | Literature | PDF opens on click, 3D effect on cover
Portfolio
|  |  | Notifications | Lists who has liked your configurations etc. |  |  | ? | This is phase 2, we can estimate this once we have more detail on the site.
|  |  | Achievements | Basic achievements included in plug-in | Basic |  | ? | This is phase 2, we can estimate this once we have more detail on the site.
|  |  | My Projects | Items displaying thumbnail of project |  |  | 20
|  |  | Custom Products | Items displaying thumbnail of configuration result |  |  | 30 | PF needs Provia to create a few example products that they want to be added to the Custom Products section
|  |  | Saved Items | Wishlist items |  |  | 35/? | Contact plugin developer if they could create this short code for a product gallery
|  |  | My Palettes | Saved Palettes |  |  | 20
|  |  | Header | Profile information |  |  | 28
|  |  | My Quiz Results | Results from Quiz, filtered by logged in users and styled
|  |  | Preferred Dealer | Choose dealer based on vicinity |  |  | 10 | We will develop functionality that will allow users to flag their preferred dealer
|  |  | Menu | Side navigation menu
|  |  | Dealer Portfolio (Our Projects) | Portfolio similar to user portfolio, "Our Projects" has dealers project photos and info